Week 2 Day 2 - Practice

1. My Main message is:

The Friday release is at risk and may move to Monday because client test environment access is still pending.

2. What Changed?

Testing identified 18 defects, 14 are fixed and retested. Four remain open and environment access promised for Wednesday has not arrived.

3. What is the problem?

Access to the latest client test environment is blocking work on two defects related to client order management system.

4. What is the impact

If access remains unavailable, the team may need to postpone the release to Monday.

5. What does the team need?

The team needs access to latest relevant test environment and confirms exactly when it be availble.

6. What happens next?

Follow up with the client to secure access time and parallelly work on the other two defects.

7. What can you leave out of the first line update?

- The client is US-based and named ABC Retail

- Defects Count 18 identified and out of which 14 has been fixed.

The key challenge is to explain in 20 seconds to Manager

Friday’s release is at risk and may move to Monday, depending on client test environment access. Access is blocking two remaining defects and other two are expected to close by Thursday. We need the client to tell us about the access so that we can reassess the release.